## Project Gantt Chart
ONLINE EXAMINATION SYSTEM - PROJECT GANTT CHART & MILESTONES
Project Duration: 6 Weeks (Sprint 1 to Sprint 3) ¦ Branch: sandesh
Task ID | Phase / Module | Task Name | Assigned To | Start Week | End Week | Duration (Wks) | Progress (%) | Wk 1-2 (Sprint 1) | Wk 3-4 (Sprint 2) | Wk 5-6 (Sprint 3)
TSK-01 | 1. Requirements | Gather User Requirements & SRS | Team Member 3 | Wk 1 | Wk 2 | 2 | 100% | 100%
TSK-02 | 1. Requirements | Define Functional & Non-Functional Specifications | Team Member 3 | Wk 1 | Wk 2 | 2 | 100% | 100%
TSK-03 | 2. Architecture | Construct System Architecture & 4 UML Diagrams | Team Member 2 | Wk 1 | Wk 2 | 2 | 100% | 100%
TSK-04 | 2. Architecture | Setup User Authentication & RBAC Middleware | Sandesh Chaudhary | Wk 1 | Wk 2 | 2 | 100% | 100%
TSK-05 | 3. Implementation | Build Question Bank & Question Manager | Team Member 2 | Wk 3 | Wk 4 | 2 | 100% |  | 100%
TSK-06 | 3. Implementation | Develop Student Exam UI & Countdown Timer | Sandesh Chaudhary | Wk 3 | Wk 4 | 2 | 100% |  | 100%
TSK-07 | 3. Implementation | Implement Background Auto-Save API Endpoint | Sandesh Chaudhary | Wk 3 | Wk 4 | 2 | 100% |  | 100%
TSK-08 | 4. Anti-Cheat & Grading | Integrate Browser Focus & Tab-Switch Proctoring | Sandesh Chaudhary | Wk 5 | Wk 6 | 2 | 100% |  |  | 100%
TSK-09 | 4. Anti-Cheat & Grading | Build Objective Question Auto-Grading Engine | Team Member 2 | Wk 5 | Wk 6 | 2 | 100% |  |  | 100%
TSK-10 | 5. Testing & Reports | Design & Execute 85 QA Test Cases Matrix | Team Member 4 | Wk 5 | Wk 6 | 2 | 100% |  |  | 100%
TSK-11 | 5. Testing & Reports | Produce Product Backlog, Gantt & Final Report | Team Member 5 | Wk 5 | Wk 6 | 2 | 100% |  |  | 100%